## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Category | User Stories / Bugs | # of Tasks | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | DONE
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
| Front-End | Create Front end | 2 | [10 empty] | 0 |  | Legend
| Front-End/Admin | Create protoype UI | 1 | [10 empty] | 0
| Admin | Create a Burndown Chart | 1 |  | 1 | [8 empty] | 1
| Data | Create SQL script | 2 |  | 1 | [8 empty] | 1
0
0
0
[14 empty] | 0 |  |  | = | Missing at Start
[14 empty] | 0 |  |  | = | Added to Sprint
[14 empty] | 0 |  |  | = | Projected Value
0
0
|  | Remaining Effort | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
|  | Ideal Trend | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | -1.2 | -1.8 | -2.4 | -3 | -3.6 |  | Change the divisor to days of remaining work to
finish sprint. Ex., if 5 days of work, divide to 5.
|  |  | Finished Sprint: | 2 |  | Remaining Sprint: | 2
Note on E5: Admin: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer. OMAF: Use this as a priority values. 1 is the lowest. MAOF: Use this as number of tasks built in each issue.
Note on R13: Coria: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on R14: Coria: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on R15: Coria: If you are only partway through a Sprint, but would like to project a completion or perform what-if analysis, use this formatting to indicate something is not yet final.